## Slide 1
This project has been funded with support from the European Commission. This publication reflects the views only of the author, and the Commission cannot be held responsible for any use which may be made of the information contained therein.
Quality assurance and monitoring
Maria Manuela Portela
Milan Gocić
23 June 2021

## Slide 2: Modifications of QAP
Strengthening of master curricula in water resources management
for the Western Balkans HEIs and stakeholders
www.swarm.ni.ac.rs
New annexes added
  Annex QA14 Course evaluation
  Annex QA15 Course evaluation report
  Annex QA16 Self-evaluation of summer/winter school
  Annex QA17 Self-evaluation of summer/winter school report

## Slide 3: WP5 – to do list
Strengthening of master curricula in water resources management
for the Western Balkans HEIs and stakeholders
www.swarm.ni.ac.rs
Quality assurance and monitoring
5.2 Regular Quality Assurance Committee meetings | 
Minutes of the meetings – UL in consultation with contact persons from all institutions First: 10 May 2019, Vienna, Second: 19 September 2019, Rijeka, ??? Sofia and Podgorica??? | 14.10.2021 IN PROGRESS
5.3 External evaluation of the project | 
Report on the external quality evaluation - UNI in consultation with contact persons from all institutions First report received on 31 August 2020 Second in August 2021 | 14.06.2020 IN PROGRESS
5.4 External financial control | 
Report on the external audit – UNI in consultation with contact persons from all institutions; First revision done 8 September 2020 Second: September 2021 | 14.11.2021 IN PROGRESS

## Slide 4: Deliverable evaluation
Strengthening of master curricula in water resources management
for the Western Balkans HEIs and stakeholders
www.swarm.ni.ac.rs
Created project deliverables should be evaluated (Annex QA13)