## Slide 1
This project has been funded with support from the European Commission. This publication reflects the views only of the author, and the Commission cannot be held responsible for any use which may be made of the information contained therein.
Project management
Milan Gocić
University of Niš
Kick-off meeting/ 21 December 2018

## Slide 2: Documents and guidelines
Strengthening of master curricula in water resources management
for the Western Balkans HEIs and stakeholders
www.swarm.ni.ac.rs
Erasmus+ programme guide
SWARM project application
Grant agreement
Partnership agreement
Guidelines for the use of the grant
Recommendations from the grant award criteria/project evaluation report and later recommendations from all other reports on project implementation
Erasmus+ Dissemination platform
Decisions, strategies, guidelines, etc. generated within the Consortium

## Slide 3: Grant agreement
Strengthening of master curricula in water resources management
for the Western Balkans HEIs and stakeholders
www.swarm.ni.ac.rs
Special conditions
Annex I – Description of the action
Annex II - General conditions
Annex III - Estimated budget of the action
Annex IV - List of beneficiaries and Mandates provided to the coordinator
Annex V - Model Technical report
Annex VI - Model Financial statement
Annex VII - Guidance notes - Report of Factual Findings on the Final Financial Report - Type II
Annex VIII – Model terms of reference for the operational verification report: not applicable
Sent to all partners

## Slide 4: Partnership agreement
Strengthening of master curricula in water resources management
for the Western Balkans HEIs and stakeholders
www.swarm.ni.ac.rs
A Partnership Agreement is a compulsory commitment that must be agreed and signed by each beneficiary organisation and should be consistent with the provisions as laid out in the Grant Agreement (and its annexes).
A copy of the Partnership Agreement will have to be provided to the Agency within 6 months of the signature of the Grant Agreement.
The Partnership Agreement must be signed by the legal representative of each of the beneficiary organisations.
The Partnership Agreement can either be multilateral (single agreement signed by the coordinator and all the other beneficiary organisations) or bilateral (a different agreement signed between the coordinator and each beneficiary organisation).

## Slide 5: Partnership agreement
Strengthening of master curricula in water resources management
for the Western Balkans HEIs and stakeholders
www.swarm.ni.ac.rs
beneficiaries' rights and obligations
beneficiaries' role and responsibilities
management and governance modalities
financial management and related rules
reporting mechanisms
conflict management mechanisms in case of problems or tasks/activities not properly implemented
communication strategy (project website, dissemination and exploitation plan)
sustainability strategy
other relevant topic for the efficient implementation of the project

## Slide 6: Role of the coordinator (Art. II.1.3)
Strengthening of master curricula in water resources management
for the Western Balkans HEIs and stakeholders
www.swarm.ni.ac.rs
Oversees the implementation of activities in line with the Grant Agreement
Ensures the respect of CBHE rules
The intermediary for all communications between the beneficiaries and the Agency including reports, payment and amendment request
Immediately provides the EACEA with the information related to any change of any of the beneficiaries or to any event likely to affect or delay the implementation of the action
Bears responsibility for supplying documents and information to the Agency which may be required

## Slide 7: Role of the coordinator (Art. II.1.3)
Strengthening of master curricula in water resources management
for the Western Balkans HEIs and stakeholders
www.swarm.ni.ac.rs
Makes the appropriate arrangements for providing any financial guarantees under the Agreements
Establishes the requests for payment in line with the Agreement
Ensures that the appropriate payments are made to the other beneficiaries without unjustified delay
Bears responsibility for providing all the necessary documents in the event of checks and audits initiated before the payment of the balance, and in the event of evaluation
Transfers to all beneficiaries, without delay, documents relating to the project.

## Slide 8: Role of the partners (Art. II.1.2)
Strengthening of master curricula in water resources management
for the Western Balkans HEIs and stakeholders
www.swarm.ni.ac.rs
Equally responsible as the coordinator
Implement activities under their responsibility
Be responsible for complying with any legal obligations incumbent on them jointly or individually
Make proper internal arrangements for the proper implementation of activities
Inform immediately the coordinator of any change likely to affect the delay in implementation, or any other change in name, address, or any legal, financial, technical, organisational or ownership situation

## Slide 9: Role of the partners (Art. II.1.2)
Strengthening of master curricula in water resources management
for the Western Balkans HEIs and stakeholders
www.swarm.ni.ac.rs
Submit in due time to the coordinator: the data needed to drew up records, financial statements or other documents; all necessary documents in the events of audits, checks or evaluation; and any other information to be provided to the Agency
Contribute to the dissemination of the projeczt results in their organisation, community and/or region
All partners including the Coordinator are responsible for promoting the fact that financing is provided from the European Union funds in the framework of the Erasmus+ programme.

## Slide 10: Financial Management
Strengthening of master curricula in water resources management
for the Western Balkans HEIs and stakeholders
www.swarm.ni.ac.rs
Pre-financings (First and Second pre financing):
first pre-financing payment of 50% of the maximum amount specified in Article I.3 of the Grant Agreement will be paid to the coordinator.
second pre-financing payment of 40% of the maximum amount specified in Article I.3 shall be paid to the coordinator, subject to the following conditions:
  having used at least 70% of the previous pre-financing instalment paid;
  the receipt of the "Statement of the costs incurred" and "Request for payment" as specified in Annex VI of the Grant Agreement;
  the receipt of a progress report on implementation of the action as specified in Annex V of the Grant Agreement.

## Slide 11: Reporting obligations/modalities
Strengthening of master curricula in water resources management
for the Western Balkans HEIs and stakeholders
www.swarm.ni.ac.rs
Reporting is a contractual obligation that has to be fulfilled by all the beneficiaries.
Although it is the coordinator's responsibility to submit the reports and their mandatory supporting documents in due time, the completion of the reports and the validation of the information they contain is a responsibility that falls under each of the beneficiaries that compose the project partnership.
In case the coordinator fails definitively to submit the project reports and the related required supporting documents, the Agency shall recover any amount already paid and if applicable, apply financial penalties of between 2% and 10% of the value of the grant as stipulated under Article II.17.1 of the Grant Agreement.

## Slide 12: Progress report on the implementation of the action
Strengthening of master curricula in water resources management
for the Western Balkans HEIs and stakeholders
www.swarm.ni.ac.rs
The progress report on the implementation of the action will have to be submitted half way through the eligibility period i.e. on 14/05/2020 at the latest.
It consists of the following:
  Technical report on the implementation of the project (description of the progress made, statistics and indicators, tables of achieved/planned outcomes, etc.)
  Summary report for publication
  Statement of the costs incurred ('intermediate Financial Statement‘)
  Request for payment of the second pre-financing (to be submitted only when 70% of the first pre-financing has been spent)

## Slide 13: Request for the second pre-financing
Strengthening of master curricula in water resources management
for the Western Balkans HEIs and stakeholders
www.swarm.ni.ac.rs
The coordinator can submit together with the "Technical report on the implementation of the project" the "Request for payment" of the second pre-financing as specified in Annex VI of the Grant Agreement in case 70% of the previous pre-financing instalment has been used.
In case 70% of the previous pre-financing instalment has not been used half way through the eligibility period, the progress report on the implementation of the action (together with the Statement of the costs actually incurred) should be submitted without the Request for payment of the second pre-financing.

## Slide 14: Reports
Strengthening of master curricula in water resources management
for the Western Balkans HEIs and stakeholders
www.swarm.ni.ac.rs
Coordinator Reports delivered to EACEA (two reports) | Progress Report – 14.05.2020
 | Final report – 14.01.2022
Partner’s Financial Report delivered to coordinator (six reports) | 1st report – 14.05.2019
 | 2nd report – 14.11.2019
 | 3rd report – 14.04.2020
 | 4th report - 14.11.2020
 | 5th report - 14.05.2021
 | 6th report - 14.11.2021
Partner’s Technical report on the implementation of the project delivered to coordinator (two reports) | 1st report – 14.04.2020
 | 2nd report – 14.10.2021

## Slide 15: Communication
Strengthening of master curricula in water resources management
for the Western Balkans HEIs and stakeholders
www.swarm.ni.ac.rs
Between Coordinator and Partners
  Defined in the Partnership Agreement
  Communication plan including means, frequency, channels
  Transparency/Documentation
With EACEA (Art. II.2)
  One Project Offcier responsible for our project
  Contact only via coordinator (Art. I.6) unless exceptional circumstances, (e.g. conflict with coordinator)
  Offcial communication to be addressed both to Project Officer and functional mailbox (EACEA-EPLUS-CBHE-PROJECTS@ec.europa.eu)

## Slide 16: Project management tasks
Strengthening of master curricula in water resources management
for the Western Balkans HEIs and stakeholders
www.swarm.ni.ac.rs
Establishment of the Steering Committee and the Project Management Committee √
Organisation of the kick-off meeting √ and coordination meetings
Development of the project management guide
Organisation of day-to-day coordination
Submission of interim and final reports

## Slide 17: WP7 activities
Strengthening of master curricula in water resources management
for the Western Balkans HEIs and stakeholders
www.swarm.ni.ac.rs
7.1 Kick-off meeting | 
Minutes of the meeting – UNI in consultation with contact persons from all institutions | 14.02.2019
7.2 Brussels kick-off meeting | 
Minutes of the meeting – UNI in consultation with contact persons from UNSA | 14.02.2019
7.3 Development of Project management guide | 
Project management guide created - UNI in consultation with contact persons from all institutions | 14.04.2019
7.4 Regular Steering Committee & Project Management meetings | 
Minutes of the meetings – UNI in consultation with contact persons from all institutions | 14.10.2021

## Slide 18: WP7 activities
Strengthening of master curricula in water resources management
for the Western Balkans HEIs and stakeholders
www.swarm.ni.ac.rs
7.5 Day-to-day coordination of project activities | 
Project correspondence - UNI in consultation with contact persons from all institutions | 14.11.2021
7.6 Submission of interim and final reports | 
Interim and final reports written and submitted to EACEA – UNI in consultation with contact persons from all institutions | 14.11.2021