## Slide 1
Project Management, Reporting and National Erasmus+ Office monitoring

## Slide 2: Content
Elements of good management models in CBHE projects
Relevant documents to be aware of…
Reports and monitoring
Additional details to be taken care of concerning financial aspects
Some challenges

## Slide 3: Elements of good project management
Awareness of Erasmus+ rules
Good planning
Clear division/delegation of tasks and responsibilities
Project teams at each of partner institutions (consisting of managing, teaching, administrative and technical staff)
Transparent decision-making procedures
Communication & continuous self-evaluation
A problem-solving approach
Support of national and institutional authorities
Appropriate dissemination of project results

## Slide 4: Good practice
Detailed partnership agreements
Efficient and easy to use communication & management tools – like Doodle, mailing lists, Google docs, Trello…
Cash flow tables
Clear instructions on how to fill the requested documents – a manual with samples
Regular internal reporting and checking of documents
Internal monitoring – use of the LFM and WP, paying attention to delivery dates

## Slide 5: Relevant documentation that all partners should be aware of:
Full text of the project proposal (including budgetary allocations)
Text of the Grant Agreement and all its annexes
Guidelines for the Use of the Grant for CBHE projects
Frequently asked questions for projects
Management is based on Grant agreement and other previously presented relevant documents, as well as on partnership agreements applicant institution is signing with all partners in the project
The account or sub-account must identify the project payments – it is highly recommended for all the partners to have separate project accounts to identify transactions more easily.
 All relevant documentation at: https://eacea.ec.europa.eu/erasmus-plus/beneficiaries-space_en

## Slide 6: Partnership agreement
The Agency provides a template with core elements that might help to draw PA
  Consistency with the GA
  Multilateral (one document signed by all partners) or Bilateral (partner A + coordinating inst.)
  Deadline - 6 months of the signature of the GA
Main topics to be covered:
  Bank accounts (beneficiary/coordinator)
  Finances & activities
  Eligible costs
  Liability
  Decision making process - voting, measures that are at disposal to the coordinator
  Ownership of the results
    all materials produced under the scope of the project must be made available for the public, in digital form, freely accessible through the Internet under open licenses
  Confidentiality & personal data protection
  Conflict of interest

## Slide 7: Financial and reporting rules
Three installments:
  1st installment - 50% of the Grant
  2nd installment - 40% of the Grant - ½ of the eligibility period following the Progress report and after having used at least 70% of the 1st installment
  3rd installment - 10% of the Grant
Transfer between budget headings is possible but not more than 10% without consent of the EACEA

## Slide 8: Financial and reporting rules
Agency shall reduce the amount of the final Grant in the event of weak implementation. Out of total 100 points the reduction of the grant will be of:
  25% if the project scores at least 40 points and below 50
  35% if the project scores at least 30 points and below 40
  55% if the project scores at least 20 points and below 300
  75% if the project scores below 20
Tendering procedure for all contracts awarded between EUR 25000 and EUR 134000
  Without splitting the purchase
Conversion into EURO of actual costs
  on the month of the first pre-financing
  on the month of the receipt of the second pre-financing
    http://ec.europa.eu/budget/contracts_grants/info_contracts/inforeuro/inforeuro_en.cfm

## Slide 9: Financial and reporting rules
Two types of costs:
Unit Costs
  Output based, "triggering event" (i.e. the fact the activity was indeed properly implemented and output produced (e.g. teaching, training)
    Staff Costs
    Travel costs - distance calculator: http://ec.europa.eu/programmes/erasmus-plus/tools/distance_en.htm
    Costs of Stay - partner/programme country mobility; for partner countries dependent of the housing country and number of days
  Real Costs
  Input based, Expenses incurred, supporting documents
    Equipment
    Sub-contracting - exceptional for services related to competences that can't be found in the consortia
    Exceptional costs
  Other types of costs:
  dissemination, publishing, overheads costs, etc. expected to be covered by co-funding

## Slide 10: Reports and monitoring by the EACEA and NEOs
Monitoring done by the National Erasmus Offices:
  Preventive* (in the first year of project implementation)
  Advisory* (after the first half of project implementation)
  Impact (after the end of the project - sustainability check)
*NEO monitoring is based on deliverable achievement

## Slide 11: NEOs monitoring
NEO reports are sent to EACEA desk officer
NEO monitoring questionnaire contains questions about:
  Implementation –are project activities being implemented on time and in line with the project application?
  Impact – at the level of departments, faculty, university….
  Sustainability – what would stay after the project is finished?
  Relevance – is project still relevant in terms of its goals and achievements?
  Partnership & Cooperation – quality of the project team and cooperation mechanisms
  Horizontal issues – Are the recommendations given by the evaluation experts/NEOs/ Agency taken into account?
Materials to be submitted to NEO Serbia usually include:
  Accurate data on institution project team
  Information on events and conferences
  Information on all relevant outcomes/outputs
  Minutes of the meetings...

## Slide 12: Some (hopefully) useful remarks
Be aware of the ineligible costs (e.g. VAT, hospitality costs, registration fees for courses, seminars, symposia, conferences, congresses, etc.)
For all questions that not clearly covered by above documents contact:
  1. EACEA desk officer
  2. NEO – project officer responsible
Communication with the EACEA goes through project coordinator
Changes during the course of the project implementation have to be reported to and/or need to be approved in advance by EACEA:
  Addition or withdrawal of co-beneficiary
  Changes of contact persons
  Changes in project work plan
  Changes in budget headings over 10%, etc...

## Slide 13: The project team “is not alone”- University/services (in Serbia) are checking:
Validity of payments before payment is done
Collecting all copies of supporting documents
Checking documents before sending them to EACEA
Use specimen of previous, successfully closed projects as a model

## Slide 14: Challenges
Purchase of the equipment – not splitting the purchase, not recorded in inventory books
Some participants may have problems with their university/faculty authorities and might ask to receive funding on their personal accounts
Some countries have complex governance in education
Different and complex national legislations
Different institutional procedures
Importance of maintaining the institutional cooperation

## Slide 15
Thank You
Foundation Tempus - Erasmus+ Office in Serbia
Ruze Jovanovic 27a, Belgrade
+381 11 33 42 430
E-mail: neo_serbia@erasmusplus.rs
www.erasmusplus.rs
Twitter: @fondacijaTempus
FB: Fondacija Tempus
Thank you for your attention