## Slide 1
This project has been funded with support from the European Commission. This publication reflects the views only of the author, and the Commission cannot be held responsible for any use which may be made of the information contained therein.
Overview of the first project year
Milan Gocić
University of Niš
Kick-off meeting/ 21 December 2018

## Slide 2: WP1 – to do list
Strengthening of master curricula in water resources management
for the Western Balkans HEIs and stakeholders
www.swarm.ni.ac.rs
Analysis of water resources management in the Western Balkan region
1.1 Identification of WB regional issues related to WRM | 
Report on WB regional issues related to WRM created – BOKU in consultation with contact persons from all WBC institutions | 14.04.2019
1.2 Analyse of EU innovations in water policy and EU recommendations and legislation in water sector | 
Report on EU water policies and innovation and EU recommendations and legislation in water sector created – BOKU in consultation with EU partners’ institutions | 14.04.2019
1.3 Analyse of existing curricula related to WRM in both EU and WB partner countries | 
Report on master curricula related to WRM in EU and WB partner countries created - BOKU in consultation with contact persons from all institutions | 14.05.2019

## Slide 3: WP1 – to do list
Strengthening of master curricula in water resources management
for the Western Balkans HEIs and stakeholders
www.swarm.ni.ac.rs
Analysis of water resources management in the Western Balkan region
1.4 Identification of needed laboratory resources in WB HEIs and alignment with formed EU HEIs WM laboratory equipment list- | 
- EU HEIs WM laboratory equipment lists created - Report on needed resources for harmonization of WB laboratory environment created – BOKU in consultation with contact persons from all institutions | 14.03.2019
1.5 Workshop on innovative practices in the EU water sector: barriers and opportunities | 
- Three-day workshop on innovative practices in the EU water sector organized (Vienna, 8-10 May 2019) - Report on innovative practices for WRM in EU created – BOKU in consultation with all institutions | 14.06.2019

## Slide 4: WP2 – to do list
Strengthening of master curricula in water resources management
for the Western Balkans HEIs and stakeholders
www.swarm.ni.ac.rs
Development of competence-based curricula aligned with EU trends
2.1 Development of specific competencies and learning outcomes of curricula in WB | 
Catalogue of competencies created – AUTh in consultation with contact persons from all institutions | 14.10.2019
2.2 Development of courses content and syllabi | 
SWARM unique set of courses developed – AUTh in consultation with all institutions | 14.01.2020
2.3 Innovation of existing and development of new master curricula for WRM in WB | 
Report on SWARM master curricula created - AUTh in consultation with contact persons from WB institutions | 14.01.2020

## Slide 5: WP2 – to do list
Strengthening of master curricula in water resources management
for the Western Balkans HEIs and stakeholders
www.swarm.ni.ac.rs
Development of competence-based curricula aligned with EU trends
2.4 Accreditation of master curricula | 
Master curricula accredited – AUTh in consultation with contact persons from all WBC institutions | 14.09.2020
2.5 Theme-based training of teaching staff for acquiring new teaching and learning methods | 
Teaching staff trained – AUTh in consultation with EU partners institutions June 2019 – UACEG (16 teaching staff), July 2019 – NMBU (16 teaching staff), September 2019 – UNIRIFCE (16 teaching staff), October 2019 – AUTH (16 teaching staff), December 2019 - UL (16 teaching staff), February 2020 - BOKU (16 teaching staff) | 14.03.2020
2.6 Purchasing of literature, software and laboratory equipment | 
Laboratories equipped - AUTh in consultation with contact persons from WB institutions | 14.11.2019

## Slide 6: WP3 – to do list
Strengthening of master curricula in water resources management
for the Western Balkans HEIs and stakeholders
www.swarm.ni.ac.rs
Development of trainings for professionals
in water sector
3.1 Introduction with LLL courses for professionals in water sector in EU | 
Report on LLL courses for professionals in EU water sector created – UPKM in consultation with contact persons from EU institutions | 14.05.2019
3.2 Analyse of water sector needs for LLL courses in WB | 
Survey of water sector needs in WB created – UPKM in consultation with WB institutions | 14.06.2019
3.3 Development of trainings’ content and corresponding educational material | 
Trainings’ material prepared – UPKM in consultation with contact persons from WB institutions | 14.03.2020

## Slide 7: WP4 – to do list
Strengthening of master curricula in water resources management
for the Western Balkans HEIs and stakeholders
www.swarm.ni.ac.rs
4.1 Implementation of developed master curricula | 
Master curricula implemented – NMBU in consultation with contact persons from WB institutions | 14.11.2021
4.2 Implementation of trainings for professionals in water sector | 
Participants trained – NMBU in consultation with contact persons from WB institutions | 14.01.2021
4.3 Self-evaluation of master curricula | 
Quality report on master curricula – NMBU in consultation with contact persons from WB institutions | 14.08.2021
4.4 Self-evaluation of trainings for professionals in water sector | 
Quality report on trainings – NMBU in consultation with contact persons from WB institutions | 14.02.2021
Implementation of developed master curricula and trainings

## Slide 8: WP5 – to do list
Strengthening of master curricula in water resources management
for the Western Balkans HEIs and stakeholders
www.swarm.ni.ac.rs
Quality assurance and monitoring
5.1 Development of the Quality and Assurance Plan | 
Quality and Assurance Plan created – UL in consultation with QAC team | 14.04.2019
5.2 Regular Quality Assurance Committee meetings | 
Minutes of the meetings – UL in consultation with contact persons from all institutions | 14.10.2021
5.3 External evaluation of the project | 
Report on the external quality evaluation - UNI in consultation with contact persons from all institutions | 14.06.2020

## Slide 9: WP5 – to do list
Strengthening of master curricula in water resources management
for the Western Balkans HEIs and stakeholders
www.swarm.ni.ac.rs
Quality assurance and monitoring
5.4 External financial control | 
Report on the external audit – UNI in consultation with contact persons from all institutions | 14.11.2021
5.5 Inter-project coaching | 
Report on the inter-project coaching – UL in consultation with contact persons from all institutions | 14.05.2020

## Slide 10: WP6 – to do list
Strengthening of master curricula in water resources management
for the Western Balkans HEIs and stakeholders
www.swarm.ni.ac.rs
Dissemination and exploitation
6.1 Creation of the Dissemination & Exploitation Plan | 
Dissemination and exploitation plan created – UNI in consultation with contact persons from all institutionsteam | 14.04.2019
6.2 Development of project website and promotional materials | 
Promotion material created – UNI in consultation with contact persons from all institutions | 14.11.2021
6.3 Info days for student enrolment | 
Info days organized - UNI in consultation with contact persons from WB institutions | 14.10.2020

## Slide 11: WP6 – to do list
Strengthening of master curricula in water resources management
for the Western Balkans HEIs and stakeholders
www.swarm.ni.ac.rs
Dissemination and exploitation
6.4 Roundtables with non-academic sector | 
Roundtables organized – UNI in consultation with contact persons from WB institutionsteam | 14.11.2020
6.5 Winter/summer schools | 
Winter/summer schools organized – UNI in consultation with contact persons from all institutions | 14.09.2021
6.6 Symposium for promoting WRM in WB | 
Report on organized symposium - UNI in consultation with contact persons from all institutions | 14.08.2021

## Slide 12: WP7 – to do list
Strengthening of master curricula in water resources management
for the Western Balkans HEIs and stakeholders
www.swarm.ni.ac.rs
7.1 Kick-off meeting | 
Minutes of the meeting – UNI in consultation with contact persons from all institutions | 14.02.2019
7.2 Brussels kick-off meeting | 
Minutes of the meeting – UNI in consultation with contact persons from UNSA | 14.02.2019
7.3 Development of Project management guide | 
Project management guide created - UNI in consultation with contact persons from all institutions | 14.04.2019
7.4 Regular Steering Committee & Project Management meetings | 
Minutes of the meetings – UNI in consultation with contact persons from all institutions | 14.10.2021
Project management

## Slide 13
Strengthening of master curricula in water resources management
for the Western Balkans HEIs and stakeholders
www.swarm.ni.ac.rs
7.5 Day-to-day coordination of project activities | 
Project correspondence - UNI in consultation with contact persons from all institutions | 14.11.2021
7.6 Submission of interim and final reports | 
Interim and final reports written and submitted to EACEA – UNI in consultation with contact persons from all institutions | 14.11.2021
WP7 – to do list
Project management