## Slide 1: WP4. Implementation of developed master curricula and trainings
This project has been funded with support from the European Commission. This publication reflects the views only of the author, and the Commission cannot be held responsible for any use which may be made of the information contained therein
Zakhar Maletskyi & Harsha Ratnaweera
progress meeting 23 June 2021
follow up of the meetings: 17 January 2021, 15 September 2020

## Slide 2: What have we promised in the application?

## Slide 3: WP4 Inputs & Outputs
WP 4
Catalogue of competences
SWARM set of courses
Equipped laboratories
6 trainings
90 WB teaching staff members trained
Materials for trainings
Dec-20/Jan-21
Self evaluations
of curricula and trainings
← Third project year →
Oct-Nov 2020
Curricula implementation
Trainings for professionals
15 Oct 2021
Students enrolled and interested
7 x 3-days trainings
210 professionals
One self-evaluation report per training
One self-evaluation report per term – twice a year
Accreditation of curricula
Professionals are interested
10-15 students per WB univ enrolled

## Slide 4: Curricula Implementation

## Slide 5: Enrolled students
University | Rough estimation / formal proof / status of studies | 
 | 15 September 2020 | Update 23 June 2021
UoNiš | 15 students at BSc – June 2021 / 5-10 MSc end of 2020 / locked until accreditation / 50:50 | 
UoNoviSad | 4-5 MSc/year – enrolment in process by end of October 2020 / online, not clear how | 4
UoSarajevo | 15 MSc – enrolment by end of 2020 / 50:50 | 7 (I year), 17 (II year)
UoMostar | 10 MSc – enrolment by October 2020 / ??? | 
UoPriština | Follow up email | 10
CollUrosevac | 15 students, awaiting accreditation | 
UoMontenegro | 5 students | 

## Slide 6: Winter / summer schools
2 students participate from SWARM project:
Format of the Summer School 2021
  Online lectures + workshops (June 2021)
  Participants of the online course: 1 week in November – decision in October (5 days funded from SWARM + co-funding from NMBU)

## Slide 7: Trainings for professionals