## Slide 1
This project has been funded with support from the European Commission. This publication reflects the views only of the author, and the Commission cannot be held responsible for any use which may be made of the information contained therein.
Overview of the first six project months and future tasks
Milan Gocić
University of Niš
First SC meeting/ 08 May 2019

## Slide 2: WP1 – to do list
Strengthening of master curricula in water resources management
for the Western Balkans HEIs and stakeholders
www.swarm.ni.ac.rs
Analysis of water resources management in the Western Balkan region
1.1 Identification of WB regional issues related to WRM | 
Report on WB regional issues related to WRM created – BOKU in consultation with contact persons from all WBC institutions | 14.04.2019 COMPLETED
1.2 Analyse of EU innovations in water policy and EU recommendations and legislation in water sector | 
Report on EU water policies and innovation and EU recommendations and legislation in water sector created – BOKU in consultation with EU partners’ institutions | 14.04.2019 COMPLETED
1.3 Analyse of existing curricula related to WRM in both EU and WB partner countries | 
Report on master curricula related to WRM in EU and WB partner countries created - BOKU in consultation with contact persons from all institutions | 14.05.2019 IN PROGRESS

## Slide 3: WP1 – to do list
Strengthening of master curricula in water resources management
for the Western Balkans HEIs and stakeholders
www.swarm.ni.ac.rs
Analysis of water resources management in the Western Balkan region
1.4 Identification of needed laboratory resources in WB HEIs and alignment with formed EU HEIs WM laboratory equipment list | 
- EU HEIs WM laboratory equipment lists created - Report on needed resources for harmonization of WB laboratory environment created – BOKU in consultation with contact persons from all institutions | 14.03.2019 COMPLETED
1.5 Workshop on innovative practices in the EU water sector: barriers and opportunities | 
- Three-day workshop on innovative practices in the EU water sector organized (Vienna, 8-10 May 2019) - Report on innovative practices for WRM in EU created – BOKU in consultation with all institutions | 14.06.2019 IN PROGRESS

## Slide 4: WP2 – to do list
Strengthening of master curricula in water resources management
for the Western Balkans HEIs and stakeholders
www.swarm.ni.ac.rs
Development of competence-based curricula aligned with EU trends
2.1 Development of specific competencies and learning outcomes of curricula in WB | 
Catalogue of competencies created – AUTh in consultation with contact persons from all institutions | 14.10.2019 IN PROGRESS
2.2 Development of courses content and syllabi | 
SWARM unique set of courses developed – AUTh in consultation with all institutions | 14.01.2020 FORTHCOMING
2.3 Innovation of existing and development of new master curricula for WRM in WB | 
Report on SWARM master curricula created - AUTh in consultation with contact persons from WB institutions | 14.01.2020 FORTHCOMING

## Slide 5: WP2 – to do list
Strengthening of master curricula in water resources management
for the Western Balkans HEIs and stakeholders
www.swarm.ni.ac.rs
Development of competence-based curricula aligned with EU trends
2.4 Accreditation of master curricula | 
Master curricula accredited – AUTh in consultation with contact persons from all WBC institutions | 14.09.2020 FORTHCOMING
2.5 Theme-based training of teaching staff for acquiring new teaching and learning methods | 
Teaching staff trained – AUTh in consultation with EU partners institutions 29-31 May 2019 – UACEG (16 teaching staff), 17-19 June 2019 – NMBU (16 teaching staff), 18-20 September 2019 – UNIRIFCE (16 teaching staff), October 2019 – AUTH (16 teaching staff), December 2019 - UL (16 teaching staff), February 2020 - BOKU (16 teaching staff) | 14.03.2020 IN PROGRESS
2.6 Purchasing of literature, software and laboratory equipment | 
Laboratories equipped - AUTh in consultation with contact persons from WB institutions | 14.11.2019 IN PROGRESS

## Slide 6: WP3 – to do list
Strengthening of master curricula in water resources management
for the Western Balkans HEIs and stakeholders
www.swarm.ni.ac.rs
Development of trainings for professionals
in water sector
3.1 Introduction with LLL courses for professionals in water sector in EU | 
Report on LLL courses for professionals in EU water sector created – UPKM in consultation with contact persons from EU institutions | 14.05.2019 IN PROGRESS
3.2 Analyse of water sector needs for LLL courses in WB | 
Survey of water sector needs in WB created – UPKM in consultation with WB institutions | 14.06.2019 IN PROGRESS
3.3 Development of trainings’ content and corresponding educational material | 
Trainings’ material prepared – UPKM in consultation with contact persons from WB institutions | 14.03.2020 FORTHCOMING

## Slide 7: WP4 – to do list
Strengthening of master curricula in water resources management
for the Western Balkans HEIs and stakeholders
www.swarm.ni.ac.rs
4.1 Implementation of developed master curricula | 
Master curricula implemented – NMBU in consultation with contact persons from WB institutions | 14.11.2021 FORTHCOMING
4.2 Implementation of trainings for professionals in water sector | 
Participants trained – NMBU in consultation with contact persons from WB institutions | 14.01.2021 FORTHCOMING
4.3 Self-evaluation of master curricula | 
Quality report on master curricula – NMBU in consultation with contact persons from WB institutions | 14.08.2021 FORTHCOMING
4.4 Self-evaluation of trainings for professionals in water sector | 
Quality report on trainings – NMBU in consultation with contact persons from WB institutions | 14.02.2021 FORTHCOMING
Implementation of developed master curricula and trainings

## Slide 8: WP5 – to do list
Strengthening of master curricula in water resources management
for the Western Balkans HEIs and stakeholders
www.swarm.ni.ac.rs
Quality assurance and monitoring
5.1 Development of the Quality and Assurance Plan | 
Quality and Assurance Plan (v05) created – UL in consultation with QAC team | 14.04.2019 COMPLETED
5.2 Regular Quality Assurance Committee meetings | 
Minutes of the meetings – UL in consultation with contact persons from all institutions First: 10 May 2019, Vienna, Second: 19 September 2019, Rijeka | 14.10.2021 IN PROGRESS
5.3 External evaluation of the project | 
Report on the external quality evaluation - UNI in consultation with contact persons from all institutions | 14.06.2020 FORTHCOMING

## Slide 9: WP5 – to do list
Strengthening of master curricula in water resources management
for the Western Balkans HEIs and stakeholders
www.swarm.ni.ac.rs
Quality assurance and monitoring
5.4 External financial control | 
Report on the external audit – UNI in consultation with contact persons from all institutions | 14.11.2021 FORTHCOMING
5.5 Inter-project coaching | 
Report on the inter-project coaching – UL in consultation with contact persons from all institutions | 14.05.2020 FORTHCOMING

## Slide 10: WP6 – to do list
Strengthening of master curricula in water resources management
for the Western Balkans HEIs and stakeholders
www.swarm.ni.ac.rs
Dissemination and exploitation
6.1 Creation of the Dissemination & Exploitation Plan | 
Dissemination and exploitation plan (v02) created – UNI in consultation with contact persons from all institutions | 14.04.2019 COMPLETED
6.2 Development of project website and promotional materials | 
Promotion material created – UNI in consultation with contact persons from all institutions | 14.11.2021 IN PROGRESS
6.3 Info days for student enrolment | 
Info days organized - UNI in consultation with contact persons from WB institutions | 14.10.2020 FORTHCOMING

## Slide 11: WP6 – to do list
Strengthening of master curricula in water resources management
for the Western Balkans HEIs and stakeholders
www.swarm.ni.ac.rs
Dissemination and exploitation
6.4 Roundtables with non-academic sector | 
Roundtables organized – UNI in consultation with contact persons from WB institutionsteam | 14.11.2020 FORTHCOMING
6.5 Winter/summer schools | 
Winter/summer schools organized – UNI in consultation with contact persons from all institutions | 14.09.2021 FORTHCOMING
6.6 Symposium for promoting WRM in WB | 
Report on organized symposium - UNI in consultation with contact persons from all institutions | 14.08.2021 FORTHCOMING

## Slide 12: WP7 – to do list
Strengthening of master curricula in water resources management
for the Western Balkans HEIs and stakeholders
www.swarm.ni.ac.rs
7.1 Kick-off meeting | 
Minutes of the meeting – UNI in consultation with contact persons from all institutions; Nis – 20-21 December 2018 | 14.02.2019 COMPLETED
7.2 Brussels kick-off meeting | 
Minutes of the meeting – UNI in consultation with contact persons from UNSA Brussels – 28-29 January 2019 | 14.02.2019 COMPLETED
7.3 Development of Project management guide | 
Project management guide (v04) created - UNI in consultation with contact persons from all institutions | 14.04.2019 COMPLETED
Project management

## Slide 13: WP7 – to do list
Strengthening of master curricula in water resources management
for the Western Balkans HEIs and stakeholders
www.swarm.ni.ac.rs
7.4 Regular Steering Committee & Project Management meetings | 
Minutes of the meetings – UNI in consultation with contact persons from all institutions First: 08/09May 2019, Vienna, Second: 18 September 2019, Rijeka | 14.10.2021 IN PROGRESS
7.5 Day-to-day coordination of project activities | 
Project correspondence - UNI in consultation with contact persons from all institutions 13 Partnership Agreements signed and sent to the EACEA | 14.11.2021 IN PROGRESS
7.6 Submission of interim and final reports | 
Interim and final reports written and submitted to EACEA – UNI in consultation with contact persons from all institutions | 14.11.2021 FORTHCOMING
Project management

## Slide 14: Preventive field monitoring visit – to do list
Strengthening of master curricula in water resources management
for the Western Balkans HEIs and stakeholders
www.swarm.ni.ac.rs
Agenda
Attendance list
Annex DE3 – Dissemination activity form
Photos
Presentations

## Slide 15: Preventive field monitoring visit
Strengthening of master curricula in water resources management
for the Western Balkans HEIs and stakeholders
www.swarm.ni.ac.rs
Kosovska Mitrovica – 20 March 2019
  First financial instalment to the Technical College of Applied Sciences should be transferred as soon as possible by the project coordinator
  Project coordinator is advised to make additional efforts to assure that all project partners purchase relevant project equipment
  Once relevant equipment is bought and installed, all HEIs have to produce equipment inventory list, which should be available for the next FM visits.
Podgorica – 15 May 2019

## Slide 16: Preventive field monitoring visit
Strengthening of master curricula in water resources management
for the Western Balkans HEIs and stakeholders
www.swarm.ni.ac.rs
Podgorica – 15 May 2019
Sarajevo

## Slide 17: First risk
Strengthening of master curricula in water resources management
for the Western Balkans HEIs and stakeholders
www.swarm.ni.ac.rs
Risk title | Purchasing of literature, software and laboratory equipment, installation and activation | 
Description of risk | Probability (unlikely, likely, most likely) Impact (low, medium, high) | Providing of equipment and adoption of law in Montenegro
Preventive action | Describe here what has to be taken into consideration to avoid that a risk occurs | Contact companies, contact ministry and NEO
Corrective action | Describe what can be done to decrease the severity and what resources will be needed | 
Decision of SC, QAC and Project Coordinator |  | 

## Slide 18: Second risk
Strengthening of master curricula in water resources management
for the Western Balkans HEIs and stakeholders
www.swarm.ni.ac.rs
Current number: 110
Final: 8 x 150 (per WB institution) = 1200
Chart: 
| UNI | UNS | UNSA | UNMO | UPKM | TCASU | UoM | PWMC VV
 | 0 | 5 | 40 | 20 | 25 | 7 | 9 | 4

## Slide 19: Second risk
Strengthening of master curricula in water resources management
for the Western Balkans HEIs and stakeholders
www.swarm.ni.ac.rs
Risk title | Analyse of water sector needs for LLL courses in WB | 
Description of risk | Probability (unlikely, likely, most likely) Impact (low, medium, high) | Inadequate number of participants
Preventive action | Describe here what has to be taken into consideration to avoid that a risk occurs | Contact companies in a better manner
Corrective action | Describe what can be done to decrease the severity and what resources will be needed | 
Decision of SC, QAC and Project Coordinator | Provide better promotion of the SWARM activities |