**RISK DESCRIPTION**

|  |  |  |
| --- | --- | --- |
| **Risk title** | Purchasing of literature, software and laboratory equipment, installation and activation | |
| **Description of risk** | **Probability**  (unlikely, **likely**, most likely)  **Impact**  (low, medium, **high**) | *Providing of equipment and adoption of law in Montenegro* |
| **Preventive action** | *Describe here what has to be taken into consideration to avoid that a risk occurs* | *Contact companies, contact ministry and NEO* |
| **Corrective action** | *Describe what can be done to decrease the severity and what resources will be needed* |  |
| **Decision of SC, QAC and Project Coordinator** |  | |



|  |  |  |
| --- | --- | --- |
| **Risk title** | Analyse of water sector needs for LLL courses in WB | |
| **Description of risk** | **Probability**  (unlikely, **likely**, most likely)  **Impact**  (low, **medium**, high) | *Inadequate number of participants* |
| **Preventive action** | *Describe here what has to be taken into consideration to avoid that a risk occurs* | *Contact companies in a better manner* |
| **Corrective action** | *Describe what can be done to decrease the severity and what resources will be needed* |  |
| **Decision of SC, QAC and Project Coordinator** | *Provide better promotion of the SWARM activities* | |

Location, date Signature

\_Nis, 25 April 2019\_\_ \_\_\_potpis.png\_\_\_\_\_\_\_\_\_

This project has been funded with support from the European Commission. This publication reflects the views only of the author, and the Commission cannot be held responsible for any use which may be made of the information contained therein.