## Slide 1
This project has been funded with support from the European Commission. This publication reflects the views only of the author, and the Commission cannot be held responsible for any use which may be made of the information contained therein.
Project activities
Milan Gocić
University of Niš
Third PMC meeting/ 15 April 2020

## Slide 2: A2.4 Accreditation of master curricula
Strengthening of master curricula in water resources management
for the Western Balkans HEIs and stakeholders
www.swarm.ni.ac.rs
Dostaviti odluku odgovarajućeg tela koje usvaja studijski program (modernizovan ili (re)akreditovan) – Savet univerziteta ili NAT – bilo bi dobro da ukoliko je moguće negde u odluci stoji da je modernizacija urađena u okviru projekta SWARM (vidite sa vašim pravnim službama da li je ovo izvodljivo)
Dostaviti elaborate studijskih programa pre i posle modernizacije ili za nove studijske programe
Dostaviti link na kojem se vidi data odluka(e) i elaborat

## Slide 3: A3.3 Development of trainings’ content and corresponding educational material
Strengthening of master curricula in water resources management
for the Western Balkans HEIs and stakeholders
www.swarm.ni.ac.rs
UPKM treba da odštampa 420 kom. priručnika (60 po WB HEI)
Videti kako da se dostavi svakoj instituciji
Kako bismo pojednostavili treninge dobro je da svaka institucija pripremi prezentaciju za poglavlje koje je pisala uz odgovarajući materijal (video, radovi i slično) koji će biti podeljen svim institucijama

## Slide 4: A4.1 Implementation of developed master curricula
Strengthening of master curricula in water resources management
for the Western Balkans HEIs and stakeholders
www.swarm.ni.ac.rs
Ukoliko je moguće upisati prvu generaciju studenata školske 2020/2021
Dostaviti 2-3 prezentacije koje se odnose na akreditovane predmete koje će postati i sastavni deo predmeta koji smo uneli u izveštaj A2.2
Nakon svakog semestra uraditi samoevaluaciju

## Slide 5: A4.3 Self-evaluation of master curricula
Strengthening of master curricula in water resources management
for the Western Balkans HEIs and stakeholders
www.swarm.ni.ac.rs
Nakon svakog semestra uraditi samoevaluaciju
Za sprovođenje samoevaluacije koristiti Annex QA5 (http://www.swarm.ni.ac.rs/activities?id=13)
Napisati izveštaj korišćenjem Annex QA6

## Slide 6: A4.2 Implementation of trainings for professionals in water sector
Strengthening of master curricula in water resources management
for the Western Balkans HEIs and stakeholders
www.swarm.ni.ac.rs
Organizovati 1 trodnevni trening period decembar 2020. – januar 2021. po mogućstvu u okviru Centra za LLL ukoliko postoji
Broj učesnika treninga 30 (po mogućstvu iz oblasti vodnih resursa)
Učesnicima obuke treba dodeliti odgovarajući sertifikat (dogovoren na nivou konzorcijuma) – videću da UNI odštampa sertifikate 7 x 40 kom.
uraditi samoevaluaciju

## Slide 7: A4.2 Implementation of trainings for professionals in water sector
Strengthening of master curricula in water resources management
for the Western Balkans HEIs and stakeholders
www.swarm.ni.ac.rs
Potrebna: agenda, slike, snimak predavanja u dužini 5-10 minuta (broj dogovor na sastanku), lista prisustnih, event report , dissemination report
Tokom treninga potrebno je uraditi samoevaluciju treninga

## Slide 8: A4.4 Self-evaluation of training
Strengthening of master curricula in water resources management
for the Western Balkans HEIs and stakeholders
www.swarm.ni.ac.rs
Nakon svakog treninga uraditi samoevaluaciju
Za sprovođenje samoevaluacije koristiti Annex QA7 (http://www.swarm.ni.ac.rs/activities?id=13)
Napisati izveštaj korišćenjem Annexa QA8

## Slide 9: A5.3 External evaluation of the project
Strengthening of master curricula in water resources management
for the Western Balkans HEIs and stakeholders
www.swarm.ni.ac.rs
UNI će uskoro pokrenuti proceduru za izbor eksternog evaluatora za ocenu ostavrenih rezultat na projektu
Evaluacija se vrši dva puta tokom trajanja projekta (najkasnije do septembra 2020. odnosno septembra 2021.) i dostavljaju se izveštaji QAC i SC timu

## Slide 10: A5.4 External financial control
Strengthening of master curricula in water resources management
for the Western Balkans HEIs and stakeholders
www.swarm.ni.ac.rs
UNI je potpisao ugovor sa revizorskom kućom iz Velike Britanije koja će raditi reviziju projekta
Finansijsku dokumentaciju dostavljati u predviđenom roku definisanim partnerskim ugovorom
Prva kontrola očekuje nas krajem aprila/početkom maja. Nakon toga na svakih 6 meseci

## Slide 11: A5.5 Inter-project coaching
Strengthening of master curricula in water resources management
for the Western Balkans HEIs and stakeholders
www.swarm.ni.ac.rs
Svaka institucija treba da predstavi neki svoj projekat (Erasmus+ ili neki drugi) na osnovu dostavljenih predloga (verzija agenda slata ranije) – sastanak Sofija – datum definišemo početkom aprila

## Slide 12: A6.2 Development of project website and promotional materials
Strengthening of master curricula in water resources management
for the Western Balkans HEIs and stakeholders
www.swarm.ni.ac.rs
Organizovati promociju projekta i ostvarenih rezultata (workshops, konferencije, seminari) i dostaviti dissemination form
Ukoliko je moguće učestvovati na nekoj televiziji ili radio emisiji ili objaviti neki rad u časopisu i dostaviti materijal
UNI štampa leaflet za promociju projekta sa mid-term rezultatima (200 po instituciji)

## Slide 13: A6.3 Info days for student enrolment
Strengthening of master curricula in water resources management
for the Western Balkans HEIs and stakeholders
www.swarm.ni.ac.rs
Organizovati promociju upisa studenata
Dostaviti slike i dissemination form
Svaka institucija treba da dizajnira brošuru i liflet za svoj program (e) koje modernizuje ili razvija nove
Svaka institucija treba da odštampa određen broj lifleta (max. 1000) i brošura (max. 500) sredstvima predviđenim finansijskim planom

## Slide 14: A6.4 Roundtables with non-academic sector
Strengthening of master curricula in water resources management
for the Western Balkans HEIs and stakeholders
www.swarm.ni.ac.rs
Organizovati jedan okrugli sto najkasnije do septembra 2020.
Broj prisutnih > 20
Dostaviti agendu, slike, listu prisutnih, event report i dissemination form
Za potrebe promocije UNI je dizajnirao liflet (na engleskom i našem jeziku) i biće odštampan u 150 kom po instituciji

## Slide 15: A6.5 Winter/summer schools sector
Strengthening of master curricula in water resources management
for the Western Balkans HEIs and stakeholders
www.swarm.ni.ac.rs
Potrebno je organizovati javni konkurs za izbor studenata koji će prisustvovati školama (1 po instituciji po školi) sa znanjem engleskog jezika i ukoliko je moguće koji su upisali nove programe
Trajanje škole 12 dana + 2 dana za put. Dostaviću primer ITRa. Nakon posete potreban dissemination form.
Three winter (January 2021 – UL and AUTH, February 2021 – UNIRIFCE) and three summer schools (June 2021 – NMBU and BOKU, July 2021 – UACEG)

## Slide 16: A6.5 Winter/summer schools sector
Strengthening of master curricula in water resources management
for the Western Balkans HEIs and stakeholders
www.swarm.ni.ac.rs
Paralelno sa školama biće organizovan i trening osoblja kako bi se videla organizacija tih škola, i to: BOKU - UNMO (1), TCASU (1), UoM (1); UACEG – UNI (2), UPKM (1); UL – UNS (1), UNSA (1), UoM (1); AUTh – UNI (2), UNSA (1); UNIRIFCE – UNI (2), UPKM (1); NMBU – UNS (1), UNMO (1)
Trajanje 5 dana + 2 dana za put. Dostaviću primer ITRa. Nakon posete potreban dissemination form
Three winter (January 2021 – UL and AUTH, February 2021 – UNIRIFCE) and three summer schools (June 2021 – NMBU and BOKU, July 2021 – UACEG)

## Slide 17: A6.6 Symposium for promoting WRM in WB sector
Strengthening of master curricula in water resources management
for the Western Balkans HEIs and stakeholders
www.swarm.ni.ac.rs
Organizator UNS, jul 2021. Broj osoba predviđen budžetom
Svako od prisutnih iz institucije treba da predstavi rezultate u okviru WRM. Možda čak i neki studentski master rad. Sledi dogovor.
UNS štampa: max. 200x proceedings for symposium, 150x agendas and ID cards for symposium
Događaju treba da prisustvuje što više ljudi sa strane radi promocije projekta i medijske kuće

## Slide 18: A7.4 Regular Steering Committee & Project Management meetings
Strengthening of master curricula in water resources management
for the Western Balkans HEIs and stakeholders
www.swarm.ni.ac.rs
Mesta održavanja: Sofija (?), Podgorica (septembar?), Lisabon (april 2021.), Solun (septembar 2021.)
Maksimalan broj osoba po instituciji je 1

## Slide 19: A7.5 Submission of interim and final reports
Strengthening of master curricula in water resources management
for the Western Balkans HEIs and stakeholders
www.swarm.ni.ac.rs
Progress report poslat 29. februara 2020. (rok za slanje je 14. maj 2020.)
Pošto sam sastavio tehnički izveštaj nije neophodno pisanje istog za svaku instituciju
Slanje finalnog izveštaja se planira za kraj novembra 2021.